## Gantt Import
Kamei Lab Project Gantt
Project name |  | Project start (auto) |  | Project end (auto) |  | Tasks | 0
Enter Start Date and End Date below. The calendar and Gantt bars update automatically. |  | Calendar starts |  | Calendar ends |  | Average progress | 0
Phase | Task | Assigned to | Start Date | End Date | Progress % | Status | Next Action

## Example
Kamei Lab Project Gantt
Project name | Example reverse-bioengineering study | Project start (auto) | 2026-09-01 | Project end (auto) | 2026-10-30 | Tasks | 6
Enter Start Date and End Date below. The calendar and Gantt bars update automatically. |  | Calendar starts | 2026-08-31 | Calendar ends | 2026-10-30 | Average progress | 35
[8 empty] | 2026-08-31 | [6 empty] | 2026-09-07 | [6 empty] | 2026-09-14 | [6 empty] | 2026-09-21 | [6 empty] | 2026-09-28 | [6 empty] | 2026-10-05 | [6 empty] | 2026-10-12 | [6 empty] | 2026-10-19 | [6 empty] | 2026-10-26
 | time axis 2026-08-31 to 2026-10-30
Phase | Task | Assigned to | Start Date | End Date | Progress % | Status | Next Action | time axis 2026-08-31 to 2026-10-30
Planning | Define research question | kk4801@nyu.edu | 2026-09-01 | 2026-09-05 | 100 | Completed | Confirm study scope | [61 empty] | 46266 | 46270
Planning | Confirm assay readouts | Team lead | 2026-09-04 | 2026-09-12 | 70 | In progress | Review pilot data | [61 empty] | 46269 | 46277
Experimental setup | Order critical materials | Lab member | 2026-09-06 | 2026-09-18 | 40 | In progress | Confirm delivery dates | [61 empty] | 46271 | 46283
Experimental setup | Run pilot experiment | Lab member | 2026-09-19 | 2026-10-02 | 0 | Not started | Finalize protocol | [61 empty] | 46284 | 46297
Analysis | Quality control and analysis | Team lead | 2026-10-03 | 2026-10-16 | 0 | Not started | Prepare analysis plan | [61 empty] | 46298 | 46311
Reporting | Team review and figure preparation | kk4801@nyu.edu | 2026-10-17 | 2026-10-30 | 0 | Not started | Schedule lab review | [61 empty] | 46312 | 46325

## Instructions
Kamei Lab Gantt Import Instructions
Step | What to do | Required | Accepted values | Web app behavior | Notes
1 | Open the Gantt Import sheet. | Yes |  | The app reads this sheet first. | Do not rename the Task, Start Date, or End Date headers.
2 | Enter one task per row. | Yes | Plain text | Each row becomes a Project Tracker milestone. | Phase may repeat across rows.
3 | Enter Assigned to. | Recommended | Member ID, NYU email, full name, or display name | Unmatched names use the default owner selected during upload. | Keep the lab roster spelling.
4 | Enter Start Date and End Date. | Yes | Excel date or yyyy-mm-dd text | The calendar, weekday headers, and Gantt bars update automatically. Missing or reversed dates are blocked before import. | The display starts on the Monday of the earliest task and continues through the latest End Date, up to 53 weeks.
5 | Enter Progress %. | No | 0 to 100 | Status is inferred when Status is blank. | 100 becomes Completed.
6 | Choose Status. | No | Not started, In progress, Blocked, Completed | The selected status is saved to Google Sheets.
7 | Upload in Project Tracker > Gantt chart. | Yes | .xlsx up to 10 MB | The app shows a preview before any write.
8 | Confirm the preview. | Yes |  | Only prior Excel-imported Gantt tasks for that project are replaced. | Manual milestones and other projects remain unchanged.
Tip | Use the Example sheet as a visual reference. |  |  |  | Copy only your own rows into Gantt Import. Project start and end cells are calculated from the task dates.

## Reference
Field | Required | Purpose | Example
Phase | No | Groups related tasks | Experimental setup
Task | Yes | Milestone or activity name | Run pilot experiment
Assigned to | Recommended | Lab roster match | kk4801@nyu.edu
Start Date | Yes | Task start | 2026-09-01
End Date | Yes | Task deadline | 2026-09-14
Progress % | No | Completion from 0 to 100 | 50
Status | No | Current task state | In progress
Next Action | No | Immediate follow-up | Review pilot data